## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Syed Moiz Ali | 2026-07-09 | Bug report submission required testing for text and file inputs. | Sprint 1 | Syed Moiz Ali | Functional | Tested text input and file upload functionality and corrected submission issues. | 2026-07-09 | Closed | Bug submission tested successfully.
2 | Syed Moiz Ali | 2026-07-10 | Historical bugs were not being retrieved correctly from the knowledge base. | Sprint 1 | Syed Moiz Ali | RAG | Updated preprocessing, generated 384-dim embeddings (embeddings_real.npy), and configured cosine similarity retrieval. | 2026-07-10 | Closed | Similar historical bugs retrieved successfully.
3 | Syed Moiz Ali | 2026-07-10 | Semantic search returned some unrelated historical bugs. | Sprint 1 | Syed Moiz Ali | AI Model | Adjusted semantic similarity retrieval and tested the results. | 2026-07-10 | Closed | Retrieval results improved after testing.
4 | Syed Moiz Ali | 2026-07-15 | Triage results required validation for different bug types. | Sprint 2 | Syed Moiz Ali | AI Model | Tested severity, priority and component classification using multiple bug reports. | 2026-07-16 | Closed | Triage outputs validated.
5 | Syed Moiz Ali | 2026-07-17 | Log Analysis Agent did not consistently extract information from different stack traces. | Sprint 2 | Syed Moiz Ali | AI Model | Improved stack-trace parsing and tested different exception types. | 2026-07-18 | Closed | Exception type and failure point extracted successfully.
6 | Syed Moiz Ali | 2026-07-19 | Agent outputs needed a consistent structure for downstream processing. | Sprint 2 | Syed Moiz Ali | Integration | Standardized outputs from Triage and Log Analysis agents. | 2026-07-20 | Closed | Structured outputs successfully passed to downstream agents.
7 | Syed Moiz Ali | 2026-07-23 | Root Cause Agent required better historical evidence. | Sprint 3 | Syed Moiz Ali | AI Model | Improved retrieval context used for root cause analysis. | 2026-07-24 | Closed | Root cause and supporting evidence displayed.
8 | Syed Moiz Ali | 2026-07-25 | Duplicate Detection required improved similarity matching. | Sprint 3 | Syed Moiz Ali | AI Model | Tuned semantic similarity search and duplicate matching. | 2026-07-26 | Closed | Similar historical bugs displayed with similarity scores.
9 | Syed Moiz Ali | 2026-07-27 | Remediation recommendations required historical bug context. | Sprint 3 | Syed Moiz Ali | AI Model | Used root cause findings and historical resolutions to generate recommendations. | 2026-07-28 | Closed | Recommended fixes displayed successfully.
10 | Syed Moiz Ali | 2026-07-29 | Multiple agent outputs needed to be displayed clearly. | Sprint 3 | Syed Moiz Ali | UI | Organized the Streamlit dashboard into separate analysis sections. | 2026-07-30 | Closed | Structured findings dashboard completed.
11 | Syed Moiz Ali | 2026-08-01 | Analytics required aggregation of processed bug results. | Sprint 4 | Syed Moiz Ali | Analytics | Implemented severity, priority, component and exception statistics. | 2026-08-02 | Closed | Analytics summary displayed successfully.
12 | Syed Moiz Ali | 2026-08-03 | Recurring root causes needed to be identified from analyzed bugs. | Sprint 4 | Syed Moiz Ali | Analytics | Added recurring root cause analysis to the analytics module. | 2026-08-04 | Closed | Recurring root causes displayed.
13 | Syed Moiz Ali | 2026-08-05 | Verified resolved bugs needed to be added to the historical knowledge base. | Sprint 4 | Syed Moiz Ali | RAG | Implemented the knowledge base growth mechanism by appending verified bug vectors directly to embeddings_real.npy and logging to SQLite. | 2026-08-06 | Closed | Verified bug successfully added to the knowledge base.
14 | Syed Moiz Ali | 2026-08-07 | Newly added bugs needed retrieval validation. | Sprint 4 | Syed Moiz Ali | RAG | Tested semantic retrieval using the newly added verified bug. | 2026-08-08 | Closed | Verified bug became available for future retrieval.
15 | Syed Moiz Ali | 2026-08-09 | Complete system required testing with different bug types. | Sprint 4 | Syed Moiz Ali | Testing | Tested five bug types including NullPointerException, FileNotFoundException, ArrayIndexOutOfBoundsException, SQLException and IOException. | 2026-08-10 | Closed | Five test cases processed successfully.
16 | Syed Moiz Ali | 2026-08-11 | Complete multi-agent pipeline required validation. | Sprint 4 | Syed Moiz Ali | Integration Testing | Validated Triage, Log Analysis, Root Cause, Duplicate Detection and Remediation outputs. | 2026-08-11 | Closed | Complete pipeline validated.
17 | Syed Moiz Ali | 2026-08-11 | Documentation required final updates. | Sprint 4 | Syed Moiz Ali | Documentation | Updated technical documentation, testing observations and project details. | 2026-08-11 | Closed | Documentation completed.
18 | Syed Moiz Ali | 2026-08-11 | Final demonstration required complete pipeline output. | Sprint 4 | Syed Moiz Ali | Demonstration | Prepared final demonstration using multiple bug submissions. | 2026-08-11 | Closed | Final demonstration prepared successfully.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others